## Sheet1 (hidden)
Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Sprint
Feature | UNI-0001 | <I> Next level | clsanche | clsanche | Low | Open | Completed (Task/Feature) | 12/15/2013 09:35:48 | 12/15/2013 09:35:48
Bug | UNI-0002 |  | eaalcara | eaalcara | Med | Blocked | Unresolved
Task | UNI-0003 |  | rhdelaro | rhdelaro | High | Development | Re-opened
Defect | UNI-0004 |  | vddelac | vddelac |  | Rejected | Fixed (Bug/Defect)
[6 empty] | Testing | Duplicate
QA
Closed

## Summary
| Type |  | Assignee | Reporter |  |  |  | Priority
Bug | 1 | clsanche | 0 | 0 |  |  | Low | 9
Defect | 0 | eaalcara | 0 | 0 |  |  | Med | 0
Feature | 8 | rhdelaro | 9 | 9 |  |  | High | 0
Task | 0 | vddelac | 0 | 0
| Status |  |  |  |  | Resolution
Open | 7 |  |  |  | Completed (Task/Feature) | 1
Blocked | 0 |  |  |  | Unresolved | 7
Development | 0 |  |  |  | Re-opened | 0
Rejected | 0 |  |  |  | Fixed (Bug/Defect) | 1
Testing | 0 |  |  |  | Duplicate | 0
QA | 0
Closed | 2

## Main
Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Details
Bug | UNI-0001 | <I> Fix bug that lets user click on the playing board (and the board updates!!) even after game result has been decided. | rhdelaro | rhdelaro | Low | Closed | Fixed (Bug/Defect) | 11/15/2013 22:37:42 | 12/15/2013 07:29:50 | Clicking anywhere on the board should not result in any update once player has won/lost.
Feature | UNI-0002 | <I> First big update. New image for buttons, updated controller logic, updated LHDataLevels, extended UIButton to LHUIButton | rhdelaro | rhdelaro | Low | Closed | Completed (Task/Feature) | 11/18/2013 06:40:18 | 12/15/2013 07:30:27
Feature | UNI-0003 | <I> Email/Feedback feature | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:23:49 |  | User button for sending email/feedback
Feature | UNI-0004 | <I> Saving/Loading/resetting progress | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:25:05 |  | Feature to save/load/reset progress
Feature | UNI-0005 | <I> Tick mark for solving levels | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:27:02 |  | Display 'check' (completed) or 'star' (completed without mistake) for each of the completed levels
Feature | UNI-0006 | <I> Achievements | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:30:43 |  | Achievements/GameCenter(?)
Feature | UNI-0007 | <I> Enable 'Settings' button | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:31:58 |  | Setting sounds and/or brightness
Feature | UNI-0008 | <I> Map of levels per difficulty | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:34:24 |  | Levels map with completion tick marks
Feature | UNI-0009 | <I> Hints | rhdelaro | rhdelaro | Low | Open | Unresolved | 12/15/2013 09:35:36 |  | Hints (for sale?)
Note on C1: <I> : IOS <A> : Andriod <J> : Java

## Example
Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Sprint
Feature | PA-0001 | <I> Summary goes here | rhdelaro | eaaclara | Low | Closed | Unresolved | 11/15/2013 20:18:44 | 11/15/2013 20:20:22
Bug |  | <A> Long summary goes here. Long summary goes here. Long summary goes here. | rhdelaro | clsanche | Med | Blocked | Unresolved | 11/15/2013 20:19:05 | 11/15/2013 20:20:26
Bug |  |  | eaaclara | vddelac | High | Closed | Completed (Task/Feature) | 11/15/2013 20:19:08 | 11/15/2013 20:29:37
Defect |  |  | vddelac | rhdelaro | Med | Testing | Unresolved | 11/15/2013 20:19:12 | 11/15/2013 20:20:47
Notes
1 | PA : PracticeArea? (UNI : Unipoles)
2 | Sprint - still undefined
Note on C1: <I> : IOS <A> : Andriod <J> : Java